Sales Data Mart Project

Client Project DE-101 | Technical Progress Documentation

# 1. Executive Summary

This project builds a reporting-oriented sales data mart from the AdventureWorksLT2022 transactional database. The goal is to provide a structured reporting layer for sales analysis, reduce repeated reporting logic, and make key metrics easier to validate.

The mart schema and five target tables have been created. The date, product, and initial customer dimensions have been populated, and 542 sales-order lines have been loaded into the sales fact table. A revenue reconciliation issue remains open: fact revenue is 708,690.1533, while the previously measured sum of SalesOrderHeader.SubTotal is 865,433.1171. The mart must not yet be described as fully validated or production-ready.

# 2. Source System and Business Rules

Source database: AdventureWorksLT2022

Source schema: SalesLT

Target schema: mart

Revenue definition in the project brief: SUM(SalesOrderDetail.LineTotal), excluding tax and freight.

Required reconciliation: total fact revenue must equal SUM(SalesOrderHeader.SubTotal), subject to an agreed currency rounding precision. The current observed results do not reconcile and require investigation before sign-off.

# 3. Target Data Mart Design

| Table | Purpose | Key design points |
| --- | --- | --- |
| mart.dim_date | Calendar attributes for reporting by date, month, quarter, and year. | date_key (YYYYMMDD), full_date, day, month, month_name, quarter, year. |
| mart.dim_product | Product reporting attributes. | Surrogate product_key; source product_id; product name/number; subcategory and parent category fields. |
| mart.dim_customer | Customer attributes and planned historical tracking. | Surrogate customer_key; source customer_id; name/company/city/country; valid_from, valid_to, is_current for SCD Type 2. |
| mart.fact_sales | Sales measures at sales-order-line grain. | sales_order_detail_id as line identifier; order ID; customer/product/date foreign keys; quantity, unit price, discount rate, revenue. |
| mart.load_log | Audit each load procedure execution. | Run ID, start/end time, row count, status, and error message. |

# 4. Work Completed So Far

Created the mart schema in AdventureWorksLT2022.

Created the five target tables: dim_date, dim_product, dim_customer, fact_sales, and load_log.

Loaded the date dimension from distinct source order dates. The current date dimension contains one row: 2008-06-01 (date_key 20080601).

Loaded 295 products into mart.dim_product, matching the profiled source product count.

Loaded 847 initial customer records into mart.dim_customer.

Loaded 542 sales-order lines into mart.fact_sales, matching the profiled SalesLT.SalesOrderDetail row count.

# 5. Current Validation Results

| Validation | Expected | Observed | Status |
| --- | --- | --- | --- |
| Source sales-order line count vs. fact row count | Equal (542) | 542 source rows; 542 fact rows | PASS for row count |
| Product dimension row count | 295 based on source profiling | 295 | PASS for count |
| Initial customer dimension count | 847 based on source profiling | 847 | PASS for initial count |
| Date dimension | Contains source order dates | 1 row: 2008-06-01 | Consistent with observed source dates; calendar coverage limited |
| Revenue reconciliation | Difference = 0.00 | Fact LineTotal sum = 708,690.1533; source SubTotal sum = 865,433.1171 | OPEN — investigate |

These are development observations, not final sign-off results. Compare SUM(SalesOrderDetail.LineTotal) with the fact revenue separately to confirm that the fact load preserved source line values. Investigate the SubTotal reconciliation difference; do not adjust values merely to force a pass.

# 6. Open Items and Risks

Investigate why SUM(mart.fact_sales.revenue) is 708,690.1533 while SUM(SalesLT.SalesOrderHeader.SubTotal) is 865,433.1171. Compare source LineTotal sum, order-level SubTotal values, join coverage, and decimal/rounding behavior.

Complete SCD Type 2 logic: detect city/country changes, expire the prior customer version, insert a new current version, and test the behavior.

Confirm which address should represent a customer (for example, Main Office, billing, or shipping). The initial-load query prioritizes Main Office and falls back to the lowest AddressID; this is a provisional assumption requiring confirmation.

Update the fact load to select the customer dimension version valid on the sales order date rather than always using the current version.

Create and test mart.usp_load_sales_mart with TRY/CATCH error handling and mart.load_log updates.

Complete 04_dq_checks.sql with check_name, expected, actual, and pass_fail columns.

Validate unmatched dimension keys, duplicate current dimension business keys, exactly one current row per customer, and idempotency after a second procedure run.

The current date dimension contains only the source order date found in this dataset. Expand to a continuous calendar if required by the reporting specification.

Previously profiled source order dates were all 2008-06-01, so month-over-month and moving-average analysis may not be meaningful with this source sample.

# 7. Day 4 Data Quality Plan

Fact row count equals source SalesOrderDetail row count.

SUM(fact revenue) reconciles to SUM(source SalesOrderHeader.SubTotal), with the difference reported at the agreed precision.

No fact rows have missing or unmatched customer, product, or date dimension keys.

No duplicate business keys among current dimension rows.

No customer has more than one row with is_current = 1.

Running the load procedure a second time leaves expected row counts unchanged.

# 8. Day 5 Business Analysis Plan

Top three products by revenue within each category using DENSE_RANK(), and explain how ROW_NUMBER() differs when ties occur.

Each category's share of total revenue using SUM() OVER().

Customer Pareto analysis: running percentage of revenue and number of customers contributing to 80% of revenue.

Each customer's revenue rank within their country.

Month-over-month revenue change and a three-month moving average, after checking source date coverage and documenting limitations.

# 9. Planned Deliverables

01_profiling.sql and profiling.md — source profiling queries and findings.

source_er_diagram.png — source entity relationship diagram.

clarification_questions.md — open business-rule questions and answers.

star_schema.png and mapping.xlsx — target design and source-to-target mapping.

02_ddl.sql — schema and table definitions.

03_usp_load_sales_mart.sql — load procedure with logging and error handling.

04_dq_checks.sql — data-quality checks returning check_name, expected, actual, pass_fail.

README.md updates documenting issues, fixes, limitations, and how to run the scripts.

Day 5 business-query script/output and status_email.md.

# 10. Suggested Status for the Lead

The initial data mart structure is in place, and the date, product, customer, and sales fact tables have been populated. The fact table contains 542 rows, matching the source sales-line count. The current revenue reconciliation check is not passing: fact revenue is 708,690.1533 versus source order subtotal revenue of 865,433.1171. I am investigating the difference before marking the mart as validated. Remaining work includes completing SCD Type 2 customer history, the load procedure and logging, rerun/idempotency tests, and the full Day 4 data-quality script.

Status: In progress — revenue reconciliation and automated-load validation remain open.